## Facebook_API
S.NO | BUG ID | DATE | Feature | BUG DESCRIPTION | SEVERITY | CURRENT STATUS |  | Dev Name | Comments | Dev Comments
1 | 9533 | 2018-08-10 | SOCIAL | Facebook REACH Metrics are not matching compare with the facebook interface | major | RESOLVED | CLOSED | Harshitha |  | In interface, the sum of reach for last 7 days or last 30 days is showing wrong values.So, Kindly check day wise
2 | 9534 | 2018-08-10 | PDF Download | In the PDF Reports Summary GA Orders Metrics alignment need to update | minor | RESOLVED | CLOSED | Harshitha |  | Issue is fixed
3 | 9535 | 2018-08-10 | PDF Download | In the PDF Reports Summary metrics icon is not good it needs to use svg images. | normal | RESOLVED | CLOSED | Harshitha |  | Issue is fixed
4 | 9536 | 2018-08-10 | SOCIAL Reach | when showing the previous time period percentage Change is Zero while no need to show the upper green symbol | normal | RESOLVED | CLOSED | Harshitha |  | Issue is fixed

## PDF Report
S.NO | BUG ID | DATE | Feature | BUG DESCRYPTION | SEVERITY | CURRENT STATUS | Dev Name
1 | 9537 | 2018-06-28 | PDF Report | Paid Channel need to remove the date range in the PDF report | normal | CLOSED
2 | 9538 | 2018-06-28 | PDF Report | Revenue Pie chart outline border is not good in the PDF report | normal | CLOSED
3 | 9539 | 2018-06-28 | PDF Report | when we download the excel unknown error alert is displaying. | normal | CLOSED
4 | 9540 | 2018-06-28 | PDF Report | impression share:-when we change the date range and download the PDF while previous download report is showing. | major | CLOSED
5 | 9541 | 2018-06-28 | PDF Report | when loading the data while we try to download the pdf unknown alert is showing. | minor | CLOSED
6 | 9542 | 2018-06-28 | PDF Report | Social summary report:- Social metrics aligment need to update in the pdf report | minor | CLOSED
7 | 9543 | 2018-06-28 | PDF Report | Social Page Likes by Day of Week Pie chart outline border is not good in the PDF report | minor | RESOLVED
8 | 9544 | 2018-06-28 | PDF Report | PDF Report:- In all channel data table font size bigger than the header its need to change. | normal | CLOSED
9 | 9545 | 2018-06-28 | PDF Report | PDF Report:- Channel wise color code is missing in the data Tables | normal | CLOSED
10 | 9546 | 2018-06-28 | PDF Report | PDF Report:-Adcopy Performance data is not available it needs to show "No Records Found" in the PDF | normal | RESOLVED
11 | 9547 | 2018-06-28 | PDF Report | PDF Report:- Adcopy performance when we Filtered date while CTR&CVR displaying decimal numbers need to update. | normal | CLOSED
12 | 9548 | 2018-06-28 | PDF Report | PDF Report:-PDF download button needs to change and to adjust the alignment | normal | CLOSED
13 | 9549 | 2018-06-28 | PDF Report | PDF Report:- when we Compare with the previous period and move to paid channel screen than we try to download the PDF while an unknown alert is showing. | normal | CLOSED
14 | 9550 | 2018-06-28 | PDF Report | PDF Report:- Unable to download PDF while we select the custom dates in the paid channel | major | CLOSED
15 | 9551 | 2018-06-28 | PDF Report | PDF Report:- when we Compare with the previous period while need to show the p1,p2 color code. | normal | CLOSED
16 |  |  | USER CREATION | when the user is adding account while account name is showing the null |  | CLOSED
17 |  |  | USER CREATION | USER CREATION:-User can add the client that client needs to assign the user but it is not showing the list of clients. |  | CLOSED
18 |  |  | USER CREATION | When we click the dashboard in the list of change view while getting the error |  | CLOSED
19 |  |  | USER CREATION | USER CREATION:-When we click the dashboard in the list of change view while getting the error |  | CLOSED
20 |  |  | USER CREATION | USER CREATION:-When we click the dashboard in the dropdow while unknown alert is showing. | minor | CLOSED
21 | 9552 | 2018-06-28 | PDF Report | PDF Report:- when data is not avaible need to show the show the alert | normal | CLOSED
22 | 9553 | 2018-06-28 | PDF Report | PDF Report:- In the adcopy pdf need to show the Total - Filtered values also | normal | CLOSED
23 | 9554 | 2018-06-28 | PDF Report | Bing account impression share data is not avilable need to show the "No Records Found" | normal | CLOSED
24 |  |  | Dashboard | paid channal:-when we compare with previous period while data is not vailable present date data also not showing | major | CLOSED
25

## WHATIF
S.NO | DATE | BUG ID | Feature | BUG DESCRYPTION | CURRENT STATUS | SEVERITY | Dev Name
1 | 2018-07-02 | 9555 | WHAT-IF ANALYSIS | Page Load Time:-actual time changed Values are not showing in the scroll bar Reply:- Crome drive should be installed in the server before deployment. It is fixed now | CLOSED | normal
2 | 2018-07-02 | 9556 | WHAT-IF ANALYSIS | when we moving the cursor in Graph Expected Revenue&Roas marks are not showing Reply:-This issue is fixed . | CLOSED | minor
3 | 2018-07-02 | 9557 | WHAT-IF ANALYSIS | when we increase the page speed time while Total order difference is miss-matching with the LXRinterface and the calculated formulas Reply:-This issue is fixed . | CLOSED | major
4 | 2018-07-02 | 9558 | WHAT-IF ANALYSIS | RoAS values are not haveing desimal when CVR, Order, AOV slider changeing time. Reply:-This issue is fixed . | CLOSED | major
5 | 2018-07-02 | 9559 | WHAT-IF ANALYSIS | In Graph Expexted ROAS and Revenue colores are same it needs to change Reply:-This issue is fixed . | CLOSED | minor
6 | 2018-07-02 | 9560 | WHAT-IF ANALYSIS | WHAT-IF ANALYSIS:- when we try to increase and decrease the CVR while new Revenue values are not showing it is displaying Unknown value( [object Object] )Reply:-This issue is fixed . | CLOSED | normal
7

## Auto Reports
S.NO | DATE | BUG ID | Feature | BUG DESCRIPTION | SEVERITY | CURRENT STATUS | cycle-2 | cycle-3 | cycle-4 | cycle-5 | Dev Name | Comments
1 | 2018-07-20 | 9561 | Account integration(Google) | In the account integration time ,removed campaigns ad groups also inserting into the database tables . | normal | RESOLVED | CLOSED |  |  |  |  | At the time of account integration for Google, we are integrating complete data(enables/paused/removed).
2 | 2018-07-24 | 9562 | Account integration (Google) | Sometimes the Google account integration is not working, it is showing the error. | major | RESOLVED | CLOSED |  |  |  |  | It is working as expected. If your network is slow, it will show that error.
3 | 2018-07-24 | 9563 | Account integration (Google) | While running the Schedulers data is not inserting the database, it's not working properly | major | RESOLVED | CLOSED |  |  |  |  | It is working as expected.
4 | 2018-07-24 | 9564 | Admin Role (MANUAL STATS DUMP) | Unable to came back Manual stats dump screen to dashboard it's getting alert | minor | RESOLVED | CLOSED |  |  |  |  | This issue is fixed.
5 | 2018-07-24 | 9565 | Auto Reports | Auto reports generating some of the reports getting exceptions (facebook reports getting exception ) like Excel Generator,904: java.lang.ArrayIndexOutOfBoundsException: 0 | major | RESOLVED | CLOSED
6 | 2018-07-24 | 9566 | Auto Reports | Some time unable to download the reports throw the non scheduler when we get the mail. | major | RESOLVED | CLOSED
7 | 2018-08-02 | 9567 | SE&GA | When we change the Metrics Source Type in the admin setting it is not updated in the dashboard all channel screen | normal |  | CLOSED |  |  |  | Harshitha - 17August
8 | 2018-08-02 | 9568 | Auto Reports (Converting Keyword Performance Report) | When we Run through the scheduler report generation ---> Converting Keyword Performance Report data is not showing | major |  | CLOSED |  |  |  | Harshitha
9 | 2018-08-02 | 9569 | Auto Reports(Top Cost Non-Converting Keyword Performance Report) | When we Run through the scheduler report generation-->Top Cost Non-Converting Keyword Performance Report data is not showing | major |  | CLOSED |  |  |  | Harshitha
10 | 2018-08-04 | 9570 | Auto Reports(SEM Weekly Report) | Please confirm SEM Weekly Reports values are showing wrong because the integrating account multiple times are something else please once check the scenarios. | major |  | CLOSED |  |  |  | Harshitha - 27 Aug
11 | 2018-08-04 | 9571 | Add client | When we adding the client,email id is not accepting. Even Though i entered correctly,It is showing like please enter valid email. | normal |  | CLOSED |  |  |  | Harshitha
12 | 2018-08-09 | 9572 | Auto Reports(SEM Monthly Report) | Year over year compare with the Previous Year showing the data is wrong | major |  | CLOSED |  |  |  | Harshitha
13 | 2018-08-09 | 9573 | Auto Reports(Facebook) | When we Integrating facebook account while inserting the stats are getting the Exception "deprecated version of the Ads API" | major |  | CLOSED |  |  |  | Harshitha
14 | 2018-08-16 | 9574 | Auto Reports(Facebook Report) | facebook/Amazon weekly and monthly reports data is miss matching compare with the interface data Except:GA Data | major |  |  | RESOLVED | CLOSED |  | Harshitha - 28 Aug
15 | 2018-08-20 | 9575 | SE&GA | Need to implement Redis in while select the Source is Search Engine | major |  |  | RESOLVED |  | RESOLVED | Harshitha - 27 Aug
16 | 2018-09-03 | 9576 | Dashboard | when we select the account and move to the setting screen then click the dashboard while selected account is not showing | normal |  |  | CLOSED |  |  | Harshitha - 30 Aug
17 | 2018-09-03 | 9577 | Auto Report | Unable to generate the custom Report and YOY Day Wise Report in testing environment it is showing the contact webmaster | major |  |  | RESOLVED | CLOSED |  | Eshwar
18 | 2018-09-03 | 9578 | Label Settings | Check the labels because campaign EXISTING LABELS names is showing multiple times in label setting page. | normal |  |  | RESOLVED | CLOSED
19 | 2018-09-04 | 9579 | SEM Weekly | SEM Weekly MTD Cost and Revenue is showing the wrong numbers | major |  |  | RESOLVED | CLOSED |  | Deekshitha
20 | 2018-09-04 | 9580 | SEM Weekly year over year | SEM Weekly year over year Ga order and revenue is missmachig compared with the interface | major |  |  | RESOLVED | CLOSED |  | Harshitha
21 | 2018-09-04 | 9581 | Dashboard | when we integrating the new account then we click the dashboard,it is showing the error | major |  |  | NEW |  | NEW
22 | 2018-09-05 | 9582 | Month Till Date Report | Google,Bing and Yahoo GA Revenue and order as more than double value | major |  |  | RESOLVED | CLOSED |  | Harshitha
23 | 2018-09-07 | 9583 | Auto Reports | YOY Day Wise Report:- GA data has zeros | major |  |  | RESOLVED | CLOSED |  | Harshitha
24 | 2018-09-07 | 9584 | Auto Reports | All Year Over Year Report CTR&CVR calculation is incorrect and it is not showinfg the % | major |  |  | RESOLVED | CLOSED |  | Harshitha
25 | 2018-09-10 | 9585 | Auto Reports | Top Cost Non-Converting Keyword count miss maching | normal |  |  | REOPEN | REOPEN | CLOSED
26 | 2018-09-18 | 9586 | Auto Reports | WOW Campaign Report Year Over Year Avg_Pos bing and yahoo getting zeros | major |  |  |  | RESOLVED | CLOSED

## Sheet7
S.NO |  | DATE | Feature | BUG DESCRIPTION | SEVERITY | CURRENT STATUS | cycle-1 | cycle-2 | cycle-3 | cycle-4 | Dev Name | Comments
1 | 9612 | 2018-10-05 | Auto Reports | Campaign Report monthly :-Avg_Pos values are getting zeros | major | NEW
2 |  | 2018-10-05 | Auto Reports

## CHANNEL-MIX
S.NO | DATE | BUG ID | Feature | BUG DESCRIPTION | SEVERITY | CURRENT STATUS | Dev Name | Comments | Dev Comments
1 | 2018-08-21 | 9587 | Channel-mix | when we increase the slider cost values it's not effective because when i increase the cost while revenue is changed is very less so please change the increase slider value. | major | RESOLVED | Harshitha - Aug 28
2 | 2018-08-21 | 9588 | Channel-mix | When we select the dashboard SE data while the channel-mix search Engines values are not showing it will happen in one time only | major | NEW
3 | 2018-08-21 | 9589 | chart | when we select the max-value in the cost and we move the mouse point in the chart while channel Revenue arrangement is changed. | normal | RESOLVED | Sri lakshmi - Sep 6
4 | 2018-08-21 | 9590 | ROAS matrix | ROAS matrix box alignment need to change it needs to show the same line. | normal | RESOLVED | Harshitha - Aug 28 |  | As per the discussion,the RoAS change will not be shown in the dashboard.
5 | 2018-08-21 | 9591 | Display the Content | Displaying the Content alignment need to change its need to arrange the broader | minor | RESOLVED | Sri lakshmi - Sep 6
6 | 2018-08-21 | 9592 | Display the Content | Channel-mix Information content need to update. | minor | RESOLVED | Sri lakshmi - Sep 6 |  | Content will be updated later
7 | 2018-08-21 | 9593 | Display the Content | Content will be the aringe the one place don't move the while channels screens are not there | normal | RESOLVED | Sri lakshmi - Sep 6